SPRINT PLANNING LOGIC FOR BOOKNEST

| Date | 26 JAN 2026 |
| --- | --- |
| Team Id | LTVIP2026TMIDS81631 |
| Project name | BOOK NEST: WHERE STORIES NESTLE |
| marks |  |

Agile Planning Logic – FlightFinder

Definitions Recap:

- Epic: Large feature (e.g., "Flight Search System")

- Story: A user-level requirement (e.g., "Apply filter by price")

- Story Point: Estimated effort using Fibonacci scale (1, 2, 3, 5…)

- Sprint Duration: 5 days

- Velocity: 12 Story Points per Sprint

Sprint 1 – (5 Days)

Epic: User Registration & Authentication

| Task | Story Points |
| --- | --- |
| Registration Form (Email/Password) | 2 |
| Gmail Registration Integration | 2 |
| LinkedIn Registration Integration | 3 |
| Email Confirmation Flow | 2 |
| OTP-based Confirmation | 3 |
| JWT Token Login System | 2 |

→ Total Story Points: 14

→ Adjust to Sprint Capacity (Velocity = 12): Include top 5 tasks (up to 12 pts), move LinkedIn to Sprint 2

Sprint 2 – (5 Days)

Epic: Booking Redirection & Admin

| Task | Story Points |
| --- | --- |
| Booking via Partner API | 5 |
| Track Booking Redirection Events | 2 |
| Admin Analytics Dashboard | 3 |
| Edit Profile & Notification Preferences | 2 |

→ Total Story Points: 12

Summary

| Sprint | Included Stories | Story Points |
| --- | --- | --- |
| Sprint 1 | Registration & Login Flows | 12 |
| Sprint 2 | Search, Filter, Alerts | 12 |
| Sprint 2 | Booking + Admin | 12 |

Team Velocity = 12 Story Points/Sprint